## Sheet1
Resolve date 3rd Feb --
1. log in using facebook -- 3rd Feb 2018
2. Address - line 2 should not be a mandatory field -- 3rd Feb
3. Upload a profile as well as boat photo of maximum 4mb -- 3rd Feb -- Max - 4mb
4. In trust and verification - When account connected with google, it still asks to connect account with google -- 3rd Feb
5. Booking for infant is also reducing the number of available seats -- 3rd Feb
6. Changes for infant is also being displayed in the booking information. -- 3rd Feb
7. Count of beds, rooms and toilets should start from 0 on add new boat page -- 3rd Feb
8. Add a mandatory star while creating a package -- 3rd Feb
9. Page not found on clicking myProfile page.-- 3rd Feb
10. Calendar not closing after selecting the date on the add package page -- 3rd Feb
11. Display location name instead of location id on admin page -- 3rd Feb
12. Boat being listed without being verified by the Admin -- Fix required -- 3rd Feb
13. length of the boat is being displayed instead of number of crew on booking page -- 3rd Feb
14. Country code not available on the checkout page -- 3rd Feb
15. Session -- 3rd Feb 2018
16. vendor booking list -- 3rd Feb 2018
17. Commission GST -- 3rd Feb
Resolve date 5th Feb --
1. Remove review button from boat booking page and put it on the past booking page -- and disable it after booking is complete -- 5th Feb
2. Put validation against the number of persons while adding a package as the number of persons should not exceed in the package than the number defined while adding the boat -- 5th Feb
3. Remove a schedule from add package page -- Not working -- 5th Feb
4. Fix the size of the box of the added schedule -- Make it constant -- 5th Feb
5. Sms verification not working -- 5th Feb
6. Update the count of the travellers on clicking the whishlist button -- 5th Feb
7. Change button to remove from wish list on successfully adding it to the wish list -- 5th Feb
Resolve date 6th Feb ---
1. Open the calendar on the booking page to change the date -- On selecting the date, open up the page to display the available time -- 6th Feb
Text changes --
1. Change text under business travel in edit profile | 1
2. Design issue for language in edit profile | 1
3. Design issue on my profile page -- missing space between address and joined date | 1
4. Text change on references page | 1
-------------
Inbox issues -- 5th/ 6th feb
Inbox is not working - Vendor is able to view the message but the customer is not.
Create groups on inbox page according to the [customer, package and the selected time] -- 5th Feb
Nothing happens on marking the message as starred.
incorrect count of messages in inbox -- 3rd Feb 2018
------------
Quoting a price in inbox -- Date to be decided